## Story Points
Story Points (Fibonacci Scale) |  |  | Points By Week
Scale: 0.5, 1, 2, 3, 5, 8, 13, 15
Story Name | Jon | Anthony | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
EPIC | 0 | 0 | Week1: 10; Week2: 10; Week3: 6; Week4: 10; Week5: 10; Week6: 9; Week7: 5
Login Process | 1 | 1
FrontEnd User Login Screen | 3 | 5
Update Admin Info | 2 | 1
FrontEnd Create User Account | 5 | 5
Retrieve Data (Remote Setup) | 5 | 2
View Employee Data | 1 | 2
View Admin Data | 3 | 2
BackEnd Create User Account | 5 | 1
Save Picture Links for the Types of Users | 1 | 1
Create Under Construction Page | 5 | 8
Connecting to Database | 3 | 5
Unique Barcode display | 1 | 1
Successful Login/Logout Pages | 3 | 5
Conceal SQL Statements | 3 | 1
Locked Account Page | 3 | 1
Incorrect Input Page | 1 | 3
Lock User Accounts | 3 | 1
Reset Attempts | 1 | 3
Reset Locked Accounts | 3 | 5
Secure Hash Algorithm | 1 | 3
Store Account Data | 1 | 1
User Login Screen | 1 | 1
Print User Results | 1 | 1
View Work Table | 1 | 1
Create User Account | 2 | 2
Responsive Webpage | 3 | 5
Display Output | 3 | 1
Registration Error | 5 | 8
Secure Website | 8 | 5
Admin Task List | 5 | 3
Store Time Data | 2 | 1
Error Redirects | 3 | 5
Content Security Policy | 5 | 3
Main System Logout | 13 | 13
Automatic Emailing | 1 | 1
Total | 106 | 106

## Points By Week
Points By Week
Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
10 | 10 | 6 | 10 | 10 | 9 | 5