## Story Points
Story Points (Fibonacci Scale)
Scale: 0.5, 1, 2, 3, 5, 8, 13, 15
Story Name | Jon | Anthony
EPIC |  | 0
Login Process |  | 1
FrontEnd User Login Screen |  | 5
Update Admin Info |  | 1
FrontEnd Create User Account |  | 5
Retrieve Data (Remote Setup) |  | 2
View Employee Data |  | 2
View Admin Data |  | 2
BackEnd Create User Account |  | 1
Save Picture Links for the Types of Users |  | 1
Create Under Construction Page |  | 8
Connecting to Database |  | 5
Unique Barcode display |  | 1
Successful Login/Logout Pages |  | 5
Conceal SQL Statements |  | 1
Locked Account Page |  | 1
Incorrect Input Page |  | 3
Lock User Accounts |  | 1
Reset Attempts |  | 3
Reset Locked Accounts |  | 5
Secure Hash Algorithm |  | 3
Store Account Data |  | 1
User Login Screen |  | 1
Print User Results |  | 1
View Work Table |  | 1
Create User Account |  | 2
Responsive Webpage |  | 5
Display Output |  | 1
Registration Error |  | 8
Secure Website |  | 5
Admin Task List |  | 3
Store Time Data |  | 1
Error Redirects |  | 5
Content Security Policy |  | 3
Main System Logout |  | 13
Automatic Emailing |  | 106
Points By Week
Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
10 | 10 | 6 | 10 | 10 | 9 | 5

## Points By Week
Points By Week
Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
10 | 10 | 6 | 10 | 10 | 9 | 5